## Burndown Chart - Overview
Burndown Chart Overview
Srpint | Period | Burned down |  | Balance
|  | Planned | Actual | Planned | Actual
| 04 of April - 03 of June | 980 | 893 | 980 | 940
1st Sprint | 04 - 18 April | 200 | 136 | 780 | 804
Low Activity | 19 April - 01 May | 60 | 49 | 720 | 755
2nd Sprint | 02 - 15 May | 120 | 95 | 600 | 660
3rd Sprint | 15 - 20 May | 120 | 150 | 480 | 510
4th Sprint | 20 -23 May | 120 | 117 | 360 | 393
5th Sprint | 23 - 26 May | 120 | 123 | 240 | 270
6th Sprint | 27 - 30 May | 120 | 125 | 120 | 145
7th Sprint | 31 May - 3 June | 120 | 98 | 0 | 47
Approximative Remaining Work |  |  |  |  | 600

## Burndown Chart - 1st Sprint
Burndown Chart 1st Sprint
Srpint | Period | Burned down |  | Balance
|  | Planned | Actual | Planned | Actual
| 04 of April - 03 of June | 200 | 136 | 980 | 940
1st Sprint | 04 - 18 April | 200 | 136 | 780 | 804
Low Activity |  |  |  | 780 | #N/A
2nd Sprint |  |  |  | 780 | #N/A
3rd Sprint |  |  |  | 780 | #N/A
4th Sprint |  |  |  | 780 | #N/A
5th Sprint |  |  |  | 780 | #N/A
6th Sprint |  |  |  | 780 | #N/A
7th Sprint |  |  |  | 780 | #N/A

## 1st Sprint Backlog
ID | Sub task | Item | People | Time | Weight (hours) | Actual Time | Actual Weight | Status
A | GIT (BitBucket / Gitkraken) setup |  |  | 3 | 15 | 7 | 35
| 1 | Setup new project + add group members | 5 | 1.5 | 7.5 | 1 | 5 | Done
| 2 | Setup GitKraken + accommodation | 5 | 1.5 | 7.5 | 2 | 10 | Done
| E | SCRUM Understaning & Errors, Logistics | 5 | 0 | 0 | 4 | 20 | Done
B | Architecture – client/server connection |  |  | 16 | 41 | 18.5 | 52
| 1 | Deciding for the connection (socket/RMI) | 5 | 0.5 | 2.5 | 0.5 | 2.5 | Done
| 2 | Deciding on the Database (local/remote) | 5 | 0.5 | 2.5 | 0.5 | 2.5 | Done
| 3 | Class Diagram | 5 | 3 | 15 | 5 | 25 | Done
| 4 | Implement Client side | 2 | 2 | 4 | 2 | 4 | Done
| 5 | Implement Server side | 2 | 2 | 4 | 2 | 4 | Done
| 6 | Implement JDBC | 1 | 3 | 3 | 3 | 3 | Done
| E | Rethink, repair and combining | 2 | 0 | 0 | 2.5 | 5 | Done
| 7 | Testing | 2 | 5 | 10 | 3 | 6 | Done
1 | As a teacher/student I want to be able to log in into the system |  |  | 16 | 35 | 21 | 51
| 1 | Class Diagram | 5 | 2 | 10 | 3 | 15 | Done
| 2 | GUI (fxml) | 2 | 1 | 2 | 1 | 2 | Done
| 3 | View Implementation | 1 | 2 | 2 | 1 | 1 | Done
| 4 | View Model Implementation | 2 | 1 | 2 | 2 | 4 | Done
| 5 | Model Impelemntation | 1 | 1 | 1 | 1 | 1 | Done
| 6 | Server Implementation | 1 | 1 | 1 | 2 | 2 | Done
| 7 | Database Implementation | 2 | 2 | 4 | 2 | 4 | Done
| 8 | Rethink, repair and combining | 5 | 1 | 5 | 2 | 10 | Done
| 9 | Testing | 2 | 2 | 4 | 3 | 6 | Done
| 10 | Documentation & Comments | 1 | 2 | 2 | 2 | 2 | Done
| 11 | Project / Process Report | 2 | 1 | 2 | 2 | 4 | Done
2 | As a teacher/student I want to be able to register into the system |  |  | 15 | 35 | 21 | 47
| 1 | Class Diagram | 5 | 2 | 10 | 2 | 10 | Done
| 2 | GUI (fxml) | 2 | 1 | 2 | 1 | 2 | Done
| 3 | View Implementation | 1 | 1 | 1 | 2 | 2 | Done
| 4 | View Model Implementation | 2 | 1 | 2 | 4 | 8 | Done
| 5 | Model Impelemntation | 1 | 1 | 1 | 2 | 2 | Done
| 6 | Server Implementation | 1 | 1 | 1 | 2 | 2 | Done
| 7 | Database Implementation | 2 | 2 | 4 | 2 | 4 | Done
| 8 | Rethink, repair and combining | 5 | 1 | 5 | 2 | 10 | Done
| 9 | Testing | 2 | 2 | 4 | 1 | 2 | Done
| 10 | Documentation & Comments | 1 | 1 | 1 | 1 | 1 | Done
| 11 | Project / Process Report | 2 | 2 | 4 | 2 | 4 | Done
3 | As a teacher I want to create a virtual classroom with unique ID |  |  | 20 | 45 | 3 | 15
| 1 | Class Diagram | 5 | 2 | 10 | 3 | 15 | Done
| 2 | GUI (fxml) | 2 | 1 | 2 | 0 | 0 | Not Started
| 3 | View Implementation | 1 | 2 | 2 | 0 | 0 | Not Started
| 4 | View Model Implementation | 2 | 2 | 4 | 0 | 0 | Not Started
| 5 | Model Impelemntation | 1 | 2 | 2 | 0 | 0 | Not Started
| 6 | Server Implementation | 1 | 2 | 2 | 0 | 0 | Not Started
| 7 | Database Implementation | 2 | 2 | 4 | 0 | 0 | Not Started
| 8 | Rethink, repair and combining | 5 | 2 | 10 | 0 | 0 | Not Started
| 9 | Testing | 2 | 2 | 4 | 0 | 0 | Not Started
| 10 | Documentation & Comments | 1 | 1 | 1 | 0 | 0 | Not Started
| 11 | Project / Process Report | 2 | 2 | 4 | 0 | 0 | Not Started
4 | As a teacher I can create and save new words in the topic |  |  | 11.5 | 29 | 0 | 0
| 1 | Class Diagram | 5 | 3 | 15 | 0 | 0 | Not Started
| 2 | GUI (fxml) | 2 | 1 | 2 | 0 | 0 | Not Started
| 3 | View Implementation | 1 | 1 | 1 | 0 | 0 | Not Started
| 4 | View Model Implementation | 2 | 2.5 | 5 | 0 | 0 | Not Started
| 5 | Model Impelemntation | 1 | 1 | 1 | 0 | 0 | Not Started
| 6 | Server Implementation | 1 | 1 | 1 | 0 | 0 | Not Started
| 7 | Database Implementation | 2 | 2 | 4 | 0 | 0 | Not Started
Total |  |  |  | 81.5 | 200 | 70.5 | 200

## Burndown Chart - Low Activity
Burndown Chart Low Activity
Srpint | Period | Burned down |  | Balance
|  | Planned | Actual | Planned | Actual
Total | 04 of April - 03 of June | 260 | 185 | 980 | 940
1st Sprint | 04 - 18 April | 200 | 136 | 780 | 804
Low Activity | 19 April - 01 May | 60 | 49 | 720 | 755
2nd Sprint |  |  |  | 720 | #N/A
3rd Sprint |  |  |  | 720 | #N/A
4th Sprint |  |  |  | 720 | #N/A
5th Sprint |  |  |  | 720 | #N/A
6th Sprint |  |  |  | 720 | #N/A
7th Sprint |  |  |  | 720 | #N/A

## Low Acivity Backlog
ID | Sub task | Item | People | Weight (hours) | Total | Used | Total Used | Status
3 | As a teacher I want to create a virtual classroom with unique ID |  |  | 19 | 36 | 21 | 39
| 1 | GUI (fxml) | 2 | 1 | 2 | 1 | 2 | Done
| 2 | View Implementation | 1 | 2 | 2 | 2 | 2 | Done
| 3 | View Model Implementation | 2 | 2 | 4 | 2 | 4 | Done
| 4 | Model Impelemntation | 1 | 2 | 2 | 2 | 2 | Done
| 5 | Server Implementation | 1 | 2 | 2 | 3 | 3 | Done
| 6 | Database Implementation | 2 | 2 | 4 | 3 | 6 | Done
| 7 | Rethink, repair and combining | 5 | 2 | 10 | 2 | 10 | Done
| 8 | Testing | 2 | 2 | 4 | 2 | 4 | Done
| 9 | Documentation & Comments | 1 | 2 | 2 | 2 | 2 | Done
| 10 | Project / Process Report | 2 | 2 | 4 | 2 | 4 | Done
4 | As a teacher can create and save a new topic in the system |  |  | 11 | 24 | 7 | 21
| 1 | Class Diagram | 5 | 2 | 10 | 3 | 15 | Done
| 2 | GUI (fxml) | 2 | 1 | 2 | 2 | 4 | Done
| 3 | View Implementation | 1 | 1 | 1 | 2 | 2 | Done
| 4 | View Model Implementation | 2 | 2 | 4 | 0 | 0 | Not Started
| 5 | Model Impelemntation | 1 | 1 | 1 | 0 | 0 | Not Started
| 6 | Server Implementation | 1 | 2 | 2 | 0 | 0 | Not Started
| 7 | Database Implementation | 2 | 2 | 4 | 0 | 0 | Not Started
Total |  |  |  | 30 | 60 | 28 | 60

## Burndown Chart - 2nd Sprint
Burndown Chart 2nd Sprint
Srpint | Period | Burned down |  | Balance
|  | Planned | Actual | Planned | Actual
Total | 04 of April - 03 of June | 380 | 280 | 980 | 940
1st Sprint | 04 - 18 April | 200 | 136 | 780 | 804
Low Activity | 19 April - 01 May | 60 | 49 | 720 | 755
2nd Sprint | 02 - 15 May | 120 | 95 | 600 | 660
3rd Sprint |  |  |  | 600 | #N/A
4th Sprint |  |  |  | 600 | #N/A
5th Sprint |  |  |  | 600 | #N/A
6th Sprint |  |  |  | 600 | #N/A
7th Sprint |  |  |  | 600 | #N/A

## 2nd Sprint Backlog
ID | Sub task | Item | People | Time | Weight (hours) | Actual Time | Actual Weight | Status
4 | As a teacher can create and save a new topic in the system |  |  | 6 | 10 | 9 | 14
| 4 | View Model Implementation | 2 | 2 | 4 | 3 | 6 | Not Started
| 5 | Model Impelemntation | 1 | 1 | 1 | 2 | 2 | Not Started
| 6 | Server Implementation | 1 | 1 | 1 | 2 | 2 | Not Started
| 7 | Database Implementation | 2 | 2 | 4 | 2 | 4 | Not Started
5 | As a teacher I can create and save new words in the topic |  |  | 15.5 | 35 | 21.5 | 51
| 1 | Class Diagram | 5 | 1 | 5 | 2 | 10 | Done
| 2 | GUI (fxml) | 2 | 0.5 | 1 | 0.5 | 1 | Done
| 3 | View Implementation | 1 | 2 | 2 | 2 | 2 | Done
| 4 | View Model Implementation | 2 | 1 | 2 | 2 | 4 | Done
| 5 | Model Impelemntation | 1 | 1 | 1 | 1.5 | 1.5 | Done
| 6 | Server Implementation | 1 | 1 | 1 | 1.5 | 1.5 | Done
| 7 | Database Implementation | 2 | 2 | 4 | 3 | 6 | Done
| 8 | Rethink, repair and combining | 5 | 2 | 10 | 3 | 15 | Done
| 9 | Testing (including test for Task 4) | 2 | 2 | 4 | 2 | 4 | Done
| 10 | Documentation & Comments (including documentation for Task 4) | 1 | 1 | 1 | 2 | 2 | Done
| 11 | Project / Process Report (including Task 4) | 2 | 2 | 4 | 2 | 4 | Done
6 | As a teacher I can edit/delete topics that are in the system |  |  | 19 | 45 | 20 | 44
| 1 | Class Diagram | 5 | 2 | 10 | 3 | 15 | Done
| 2 | GUI (fxml) | 2 | 1 | 2 | 2 | 4 | Done
| 3 | View Implementation | 1 | 2 | 2 | 3 | 3 | Done
| 4 | View Model Implementation | 2 | 2 | 4 | 2 | 4 | Done
| 5 | Model Impelemntation | 1 | 1 | 1 | 2 | 2 | Done
| 6 | Server Implementation | 1 | 1 | 1 | 2 | 2 | Done
| 7 | Database Implementation | 2 | 3 | 6 | 2 | 4 | Done
| 8 | Rethink, repair and combining | 5 | 2 | 10 | 1 | 5 | Done
| 9 | Testing | 2 | 2 | 4 | 1 | 2 | Done
| 10 | Documentation & Comments | 1 | 1 | 1 | 1 | 1 | Done
| 11 | Project / Process Report | 2 | 2 | 4 | 1 | 2 | Done
7 | As a teacher I want be able to edit/delete words that are in the topics |  |  | 12.5 | 30 | 2 | 10
| 1 | Class Diagram | 5 | 2 | 10 | 2 | 10 | Started
| 2 | GUI (fxml) | 2 | 1 | 2 | 0 | 0 | Not Started
| 3 | View Implementation | 1 | 2 | 2 | 0 | 0 | Not Started
| 4 | View Model Implementation | 2 | 2 | 4 | 0 | 0 | Not Started
| 5 | Model Impelemntation | 1 | 1 | 1 | 0 | 0 | Not Started
| 6 | Server Implementation | 1 | 1 | 1 | 0 | 0 | Not Started
| 7 | Database Implementation | 2 | 2.5 | 5 | 0 | 0 | Not Started
| 8 | Rethink, repair and combining | 5 | 1 | 5 | 0 | 0 | Not Started
Total |  |  |  | 53 | 120 | 52.5 | 119

## Burndown Chart - 3rd Sprint
Burndown Chart 3rd Sprint
Srpint | Period | Burned down |  | Balance
|  | Planned | Actual | Planned | Actual
Total | 04 of April - 03 of June | 500 | 430 | 980 | 940
1st Sprint | 04 - 18 April | 200 | 136 | 780 | 804
Low Activity | 19 April - 01 May | 60 | 49 | 720 | 755
2nd Sprint | 02 - 15 May | 120 | 95 | 600 | 660
3rd Sprint | 15 - 20 May | 120 | 150 | 480 | 510
4th Sprint |  |  |  | 480 | #N/A
5th Sprint |  |  |  | 480 | #N/A
6th Sprint |  |  |  | 480 | #N/A
7th Sprint |  |  |  | 480 | #N/A

## 3rd Sprint Backlog
ID | Sub task | Item | People | Time | Weight (hours) | Actual Time | Actual Weight | Status
7 | As a teacher I want be able to edit/delete words that are in the topics |  |  | 18.5 | 40 | 13 | 31
| 1 | Class Diagram | 5 | 2 | 10 | 1 | 5 | Done
| 2 | GUI (fxml) | 2 | 1 | 2 | 1 | 2 | Done
| 3 | View Implementation | 1 | 2 | 2 | 1 | 1 | Done
| 4 | View Model Implementation | 2 | 2 | 4 | 1 | 2 | Done
| 5 | Model Impelemntation | 1 | 1 | 1 | 1 | 1 | Done
| 6 | Server Implementation | 1 | 1 | 1 | 1 | 1 | Done
| 7 | Database Implementation | 2 | 2.5 | 5 | 2 | 4 | Done
| 8 | Rethink, repair and combining | 5 | 1 | 5 | 2 | 10 | Done
| 9 | Testing | 2 | 2 | 4 | 1 | 2 | Done
| 10 | Documentation & Comments | 1 | 2 | 2 | 1 | 1 | Done
| 11 | Project / Process Report | 2 | 2 | 4 | 1 | 2 | Done
8 | As a teacher I want to be able to create a session specifying the virtual classroom it will be assigned to, a topic and a number of words from the word list provided by the selected topic |  |  | 23.5 | 65 | 17.5 | 44
| 1 | Class Diagram | 5 | 3 | 15 | 2 | 10 | Done
| 2 | GUI (fxml) | 2 | 2 | 4 | 1 | 2 | Done
| 3 | View Implementation | 1 | 1 | 1 | 1 | 1 | Done
| 4 | View Model Implementation | 2 | 1 | 2 | 1 | 2 | Done
| 5 | Model Impelemntation | 1 | 2 | 2 | 2 | 2 | Done
| 6 | Server Implementation | 1 | 2 | 2 | 2 | 2 | Done
| 7 | Database Implementation | 2 | 2.5 | 5 | 2.5 | 5 | Done
| 8 | Rethink, repair and combining | 5 | 5 | 25 | 3 | 15 | Done
| 9 | Testing | 2 | 2 | 4 | 1 | 2 | Done
| 10 | Documentation & Comments | 1 | 1 | 1 | 1 | 1 | Done
| 11 | Project / Process Report | 2 | 2 | 4 | 1 | 2 | Done
9 | The system to generate an unique access code for each session (and display) |  |  | 6 | 15 | 7.5 | 17.5
| 1 | Class Diagram | 5 | 1 | 5 | 1 | 5 | Done
| 2 | GUI (fxml) | 1 | 0.5 | 0.5 | 0.5 | 0.5 | Done
| 3 | View Implementation | 1 | 0.5 | 0.5 | 0.5 | 0.5 | Done
| 4 | View Model Implementation | 2 | 0.5 | 1 | 0.5 | 1 | Done
| 5 | Model Impelemntation | 1 | 0.5 | 0.5 | 1 | 1 | Done
| 6 | Server Implementation | 1 | 1.5 | 1.5 | 1 | 1 | Done
| 7 | Database Implementation | 2 | 0.5 | 1 | 0.5 | 1 | Done
| 8 | Rethink, repair and combining | 5 | 1 | 5 | 1 | 5 | Done
| 9 | Testing | 2 | 0 | 0 | 0.5 | 1 | Done
| 10 | Documentation & Comments | 1 | 0 | 0 | 0.5 | 0.5 | Done
| 11 | Project / Process Report | 2 | 0 | 0 | 0.5 | 1 | Done
10 | As a student should be able to join a session using a provided access code |  |  | 0 | 0 | 7.5 | 27.5
| 1 | Class Diagram | 5 | 0 | 0 | 5 | 25 | Done
| 2 | GUI (fxml) | 1 | 0 | 0 | 2.5 | 2.5 | Done
Total |  |  |  | 48 | 120 | 45.5 | 120

## Burndown Chart - 4th Sprint
Burndown Chart 4th Sprint
Srpint | Period | Burned down |  | Balance
|  | Planned | Actual | Planned | Actual
Total | 04 of April - 03 of June | 620 | 547 | 980 | 940
1st Sprint | 04 - 18 April | 200 | 136 | 780 | 804
Low Activity | 19 April - 01 May | 60 | 49 | 720 | 755
2nd Sprint | 02 - 15 May | 120 | 95 | 600 | 660
3rd Sprint | 15 - 20 May | 120 | 150 | 480 | 510
4th Sprint | 20 -23 May | 120 | 117 | 360 | 393
5th Sprint |  |  |  | 360 | #N/A
6th Sprint |  |  |  | 360 | #N/A
7th Sprint |  |  |  | 360 | #N/A

## 4th Sprint Backlog
ID | Sub task | Item | People | Time | Weight (hours) | Actual Time | Actual Weight | Status
10 | As a student should be able to join a session using a provided access code |  |  | 26 | 55 | 27 | 60
| 3 | View Implementation | 1 | 4 | 4 | 4 | 4 | Done
| 4 | View Model Implementation | 2 | 3 | 6 | 3 | 6 | Done
| 5 | Model Impelemntation | 1 | 2 | 2 | 2 | 2 | Done
| 6 | Server Implementation | 1 | 4 | 4 | 4 | 4 | Done
| 7 | Database Implementation | 2 | 3 | 6 | 3 | 6 | Done
| 8 | Rethink, repair and combining | 5 | 5 | 25 | 6 | 30 | Done
| 9 | Testing | 2 | 2 | 4 | 2 | 4 | Done
| 10 | Documentation & Comments | 1 | 2 | 2 | 2 | 2 | Done
| 11 | Project / Process Report | 2 | 1 | 2 | 1 | 2 | Done
11 | As a teacher I want to be able to see what students are currently connected to a session |  |  | 25.5 | 65 | 24.75 | 60
| 1 | Class Diagram | 5 | 3 | 15 | 2 | 10 | Done
| 2 | GUI (fxml) | 1 | 1 | 1 | 2 | 2 | Done
| 3 | View Implementation | 1 | 3 | 3 | 3 | 3 | Done
| 4 | View Model Implementation | 2 | 2 | 4 | 2.5 | 5 | Done
| 5 | Model Impelemntation | 1 | 2 | 2 | 2 | 2 | Done
| 6 | Server Implementation | 1 | 3 | 3 | 3.5 | 3.5 | Done
| 7 | Database Implementation | 2 | 3.5 | 7 | 4 | 8 | Done
| 8 | Rethink, repair and combining | 5 | 5 | 25 | 5 | 25 | Done
| 9 | Testing | 2 | 1 | 2 | 0.75 | 1.5 | Started
| 10 | Documentation & Comments | 1 | 1 | 1 | 0 | 0 | Not Started
| 11 | Project / Process Report | 2 | 1 | 2 | 0 | 0 | Not Started
Total |  |  |  | 51.5 | 120 | 51.75 | 120

## Burndown Chart - 5th Sprint
Burndown Chart 5th Sprint
Srpint | Period | Burned down |  | Balance
|  | Planned | Actual | Planned | Actual
Total | 04 of April - 03 of June | 740 | 670 | 980 | 940
1st Sprint | 04 - 18 April | 200 | 136 | 780 | 804
Low Activity | 19 April - 01 May | 60 | 49 | 720 | 755
2nd Sprint | 02 - 15 May | 120 | 95 | 600 | 660
3rd Sprint | 15 - 20 May | 120 | 150 | 480 | 510
4th Sprint | 20 -23 May | 120 | 117 | 360 | 393
5th Sprint | 23 - 26 May | 120 | 123 | 240 | 270
6th Sprint |  |  |  | 240 | #N/A
7th Sprint |  |  |  | 240 | #N/A

## 5th Sprint Backlog
ID | Sub task | Item | People | Time | Weight (hours) | Actual Time | Actual Weight | Status
11 | As a teacher I want to be able to see what students are currently connected to a session |  |  | 2 | 3 | 3 | 4
| 10 | Documentation & Comments | 1 | 1 | 1 | 2 | 2 | Done
| 11 | Project / Process Report | 2 | 1 | 2 | 1 | 2 | Done
12 | The student must be able to select only one word from a provided list of words, given that the word was not selected by another student |  |  | 28 | 75 | 25.5 | 68
| 1 | Class Diagram | 5 | 4 | 20 | 3 | 15 | Done
| 2 | GUI (fxml) | 1 | 2 | 2 | 2 | 2 | Done
| 3 | View Implementation | 1 | 4 | 4 | 3 | 3 | Done
| 4 | View Model Implementation | 2 | 3 | 6 | 3 | 6 | Done
| 5 | Model Impelemntation | 1 | 2 | 2 | 2 | 2 | Done
| 6 | Server Implementation | 1 | 2 | 2 | 1.5 | 1.5 | Done
| 7 | Database Implementation | 2 | 2 | 4 | 1.5 | 3 | Done
| 8 | Rethink, repair and combining | 5 | 6 | 30 | 6 | 30 | Done
| 9 | Testing | 2 | 1 | 2 | 1 | 2 | Done
| 10 | Documentation & Comments | 1 | 1 | 1 | 1.5 | 1.5 | Done
| 11 | Project / Process Report | 2 | 1 | 2 | 1 | 2 | Done
13 | As a student I want to be to enter the question |  |  | 18 | 45 | 17 | 43
| 1 | Class Diagram | 5 | 2 | 10 | 2 | 10 | Done
| 2 | GUI (fxml) | 1 | 1 | 1 | 1 | 1 | Done
| 3 | View Implementation | 1 | 1 | 1 | 1 | 1 | Done
| 4 | View Model Implementation | 2 | 2 | 4 | 2 | 4 | Done
| 5 | Model Impelemntation | 1 | 1 | 1 | 1 | 1 | Done
| 6 | Server Implementation | 1 | 2 | 2 | 2 | 2 | Done
| 7 | Database Implementation | 2 | 3 | 6 | 2 | 4 | Done
| 8 | Rethink, repair and combining | 5 | 3 | 15 | 3 | 15 | Done
| 9 | Testing | 2 | 1 | 2 | 1 | 2 | Done
| 10 | Documentation & Comments | 1 | 1 | 1 | 1 | 1 | Done
| 11 | Project / Process Report | 2 | 1 | 2 | 1 | 2 | Done
14 | As a student I want be able to specify the type of question from a provided list and enter the four possible answers specifying the correct one |  |  | 0 | 0 | 1 | 5
| 1 | Class Diagram | 5 | 0 | 0 | 1 | 5 | Started
Total |  |  |  | 48 | 123 | 46.5 | 120

## Burndown Chart - 6th Sprint
Burndown Chart 7th Sprint
Srpint | Period | Burned down |  | Balance
|  | Planned | Actual | Planned | Actual
Total | 04 of April - 03 of June | 860 | 795 | 980 | 940
1st Sprint | 04 - 18 April | 200 | 136 | 780 | 804
Low Activity | 19 April - 01 May | 60 | 49 | 720 | 755
2nd Sprint | 02 - 15 May | 120 | 95 | 600 | 660
3rd Sprint | 15 - 20 May | 120 | 150 | 480 | 510
4th Sprint | 20 -23 May | 120 | 117 | 360 | 393
5th Sprint | 23 - 26 May | 120 | 123 | 240 | 270
6th Sprint | 27 - 30 May | 120 | 125 | 120 | 145
7th Sprint |  |  |  | 120 | #N/A

## 6th Sprint Backlog
ID | Sub task | Item | People | Time | Weight (hours) | Actual Time | Actual Weight | Status
14 | As a student I want be able to specify the type of question from a provided list and enter the four possible answers specifying the correct one |  |  | 24 | 60 | 19 | 43
| 1 | Class Diagram | 5 | 2 | 10 | 1.5 | 7.5 | Done
| 2 | GUI (fxml) | 1 | 2 | 2 | 1 | 1 | Done
| 3 | View Implementation | 1 | 2 | 2 | 1.5 | 1.5 | Done
| 4 | View Model Implementation | 2 | 2 | 4 | 1.5 | 3 | Done
| 5 | Model Impelemntation | 1 | 2 | 2 | 2 | 2 | Done
| 6 | Server Implementation | 1 | 2 | 2 | 2 | 2 | Done
| 7 | Database Implementation | 2 | 3 | 6 | 2.5 | 5 | Done
| 8 | Rethink, repair and combining | 5 | 5 | 25 | 3 | 15 | Done
| 9 | Testing | 2 | 2 | 4 | 1 | 2 | Done
| 10 | Documentation & Comments | 1 | 1 | 1 | 2 | 2 | Done
| 11 | Project / Process Report | 2 | 1 | 2 | 1 | 2 | Done
15 | As a student I want to be able to see a summary of the question |  |  | 17 | 35 | 15.5 | 37
| 1 | Class Diagram | 5 | 1 | 5 | 1 | 5 | Done
| 2 | GUI (fxml) | 1 | 1 | 1 | 1 | 1 | Done
| 3 | View Implementation | 1 | 1 | 1 | 1 | 1 | Done
| 4 | View Model Implementation | 2 | 2 | 4 | 1 | 2 | Done
| 5 | Model Impelemntation | 1 | 2 | 2 | 1 | 1 | Done
| 6 | Server Implementation | 1 | 2 | 2 | 2 | 2 | Done
| 7 | Database Implementation | 2 | 2 | 4 | 2.5 | 5 | Done
| 8 | Rethink, repair and combining | 5 | 2 | 10 | 3 | 15 | Done
| 9 | Testing | 2 | 1 | 2 | 1 | 2 | Done
| 10 | Documentation & Comments | 1 | 2 | 2 | 1 | 1 | Done
| 11 | Project / Process Report | 2 | 1 | 2 | 1 | 2 | Done
16 | As a student I want to be able to submit the question for review |  |  | 11 | 25 | 13 | 40
| 1 | Class Diagram | 5 | 3 | 15 | 3 | 15 | Done
| 2 | GUI (fxml) | 1 | 1 | 1 | 0.5 | 0.5 | Done
| 3 | View Implementation | 1 | 1 | 1 | 0.5 | 0.5 | Done
| 4 | View Model Implementation | 2 | 2 | 4 | 1 | 2 | Done
| 5 | Model Impelemntation | 1 | 2 | 2 | 1 | 1 | Done
| 6 | Server Implementation | 1 | 2 | 2 | 2 | 2 | Done
| 7 | Database Implementation | 2 | 0 | 0 | 2 | 4 | Done
| 8 | Rethink, repair and combining | 5 | 0 | 0 | 3 | 15 | Done
Total |  |  |  | 52 | 120 | 47.5 | 120

## Burndown Chart - 7th Sprint
Burndown Chart 7th Sprint
Srpint | Period | Burned down |  | Balance
|  | Planned | Actual | Planned | Actual
Total | 04 of April - 03 of June | 980 | 893 | 980 | 940
1st Sprint | 04 - 18 April | 200 | 136 | 780 | 804
Low Activity | 19 April - 01 May | 60 | 49 | 720 | 755
2nd Sprint | 02 - 15 May | 120 | 95 | 600 | 660
3rd Sprint | 15 - 20 May | 120 | 150 | 480 | 510
4th Sprint | 20 -23 May | 120 | 117 | 360 | 393
5th Sprint | 23 - 26 May | 120 | 123 | 240 | 270
6th Sprint | 27 - 30 May | 120 | 125 | 120 | 145
7th Sprint | 31 May - 3 June | 120 | 98 | 0 | 47

## 7th Sprint Backlog
ID | Sub task | Item | People | Time | Weight (hours) | Actual Time | Actual Weight | Status
16 | As a student I want to be able to submit the question for review |  |  | 5 | 8 | 5 | 8
| 9 | Testing | 2 | 2 | 4 | 2 | 4 | Done
| 10 | Documentation & Comments | 1 | 2 | 2 | 2 | 2 | Done
| 11 | Project / Process Report | 2 | 1 | 2 | 1 | 2 | Done
17 | As a teacher I want to be able to see a list of submitted questions ready for review(live) |  |  | 17 | 45 | 21 | 54
| 1 | Class Diagram | 5 | 3 | 15 | 3 | 15 | Done
| 2 | GUI (fxml) | 1 | 1 | 1 | 1 | 1 | Done
| 3 | View Implementation | 1 | 1 | 1 | 2 | 2 | Done
| 4 | View Model Implementation | 2 | 1 | 2 | 2 | 4 | Done
| 5 | Model Impelemntation | 1 | 1 | 1 | 1 | 1 | Done
| 6 | Server Implementation | 1 | 3 | 3 | 3 | 3 | Done
| 7 | Database Implementation | 2 | 1 | 2 | 1 | 2 | Done
| 8 | Rethink, repair and combining | 5 | 3 | 15 | 4 | 20 | Done
| 9 | Testing | 2 | 1 | 2 | 1 | 2 | Done
| 10 | Documentation & Comments | 1 | 1 | 1 | 2 | 2 | Done
| 11 | Project / Process Report | 2 | 1 | 2 | 1 | 2 | Done
18 | As a teacher I want to be able to select a specific question displayed |  |  | 19 | 45 | 23.5 | 58
| 1 | Class Diagram | 5 | 2 | 10 | 3 | 15 | Done
| 2 | GUI (fxml) | 1 | 2 | 2 | 2 | 2 | Done
| 3 | View Implementation | 1 | 2 | 2 | 2 | 2 | Done
| 4 | View Model Implementation | 2 | 2 | 4 | 1.5 | 3 | Done
| 5 | Model Impelemntation | 1 | 1 | 1 | 2 | 2 | Done
| 6 | Server Implementation | 1 | 1 | 1 | 2 | 2 | Done
| 7 | Database Implementation | 2 | 2 | 4 | 3 | 6 | Done
| 8 | Rethink, repair and combining | 5 | 3 | 15 | 4 | 20 | Done
| 9 | Testing | 2 | 1 | 2 | 1 | 2 | Done
| 10 | Documentation & Comments | 1 | 2 | 2 | 2 | 2 | Done
| 11 | Project / Process Report | 2 | 1 | 2 | 1 | 2 | Done
19 | As a teacher I want be able to accept/reject a question and give feedback if needed |  |  | 8 | 22 | 0 | 0
| 1 | Class Diagram | 5 | 3 | 15 | 0 | 0 | Started
| 2 | GUI (fxml) | 1 | 1 | 1 | 0 | 0 | Not Started
| 3 | View Implementation | 1 | 1 | 1 | 0 | 0 | Not Started
| 4 | View Model Implementation | 2 | 2 | 4 | 0 | 0 | Not Started
| 5 | Model Impelemntation | 1 | 1 | 1 | 0 | 0 | Not Started
Total |  |  |  | 49 | 120 | 49.5 | 120